## Project Planner
VRShop Locator
[5 empty] | week 1 starts at: | Nov. 18,2019
TASK | Ahrve Kim E. Jabonillo | TASK | Jucel A. Gadiano | TASK | Benny Pañares | WEEKS | Date
Approach for cancelation and approval Re-Designing another project |  | Approach for cancelation and approval Re-Designing another project |  | Approach for cancelation and approval Re-Designing another project |  | 1 | Nov. 25-29,2019
Team Orientation and Planning |  | Team Orientation and Planning |  | Team Orientation and Planning |  | 2 | Dec. 2-6,2019
Researching of what will we use in our project |  | Gathering Information of the shop |  | Gathering Information of the shop |  | 3 | Dec. 9-13,2019
Installing Required Software Application and Searching about React Native |  | Gathering Information of the shop |  | Gathering Information of the shop |  | 4 | Dec. 16-20,2019
Researching how to use maps and Creating maps in Andriod |  | Researching how to use maps and making the statement of the problem in our documents |  | Researching how to use maps and making the statement of the problem in our documents |  | 5
Researching of laravel vue and Creating an login account |  | Researching of React Native and Laravel |  | Researching of React Native and Laravel |  | 6
Creating Web for the Admin with datebase |  | Creating Web for the Admin |  | Creating Web for the Admin |  | 7
Researching of routing of pages and Applying it |  | Making some Documents |  | Creating of sample android |  | 8
Creating a web of Adding Location of the shops which can edit and add |  | Gathering Information of the shop |  | Gathering Information of the shop |  | 9
Fixing or debugging on our website testing and re-test |  | Assisting fixing bugs |  | Assisting fixing bugs |  | 10
Learning more about React native and monitoring and finalizing our website |  | Learning more about React-native and assiting fixing errors |  | Learning more about React-native and assiting fixing errors |  | 11
Creating our Application and calling data in the database |  | Creating maps and calling from the data base |  | Creating maps and calling from the data base |  | 12
Finalizing and hard testing in our application |  | Paperworks and Documentation |  | Paperworks and Documentation |  | 13